## Screen Comparison
TRACKLYNK LITE — SCREEN × FEATURE COMPARISON vs BOUNCIE
Screen-level breakdown · Feature vs Bouncie · UX / Dev build status · April 2026
| ✓ Done |  | ◑ Partial (UI/mock) |  | ↓ Dev columns — fill after Nash prioritization |  |  |  | ✗ Not Built
|  |  |  | Dev key → | ✓ Done | ◑ In Progress | ✗ Not Started | P0 / P1 / P2
# | Screen | Feature | Bouncie | UX (Shobhit) | Frontend Web | Frontend Native | Backend | Priority | Phase | Notes / Gap Analysis
HOME / MAP
1 | Home / Map | Vehicle pin on live map | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Map renders via Google Maps. Pin exists. No live GPS data — mock coordinates only.
2 | Home / Map | Live GPS refresh (15-second via 4G LTE-M) | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | No polling or WebSocket. Map is static after load. Critical for core value prop.
3 | Home / Map | Parked status chip + last engine-off timestamp | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | "Parked" status text shown. Hardcoded. Needs real engine-off event from API.
4 | Home / Map | Current parked address (reverse-geocoded) | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Address text shown on Home.jsx. Hardcoded placeholder string.
5 | Home / Map | NWS severe weather badge on map | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P2 | V2 | Bouncie shows NWS badge prominently on map. Not started. Needs NWS API integration.
6 | Home / Map | Vehicle card (name, model, year) | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Card renders with mock "Toyota Tacoma 2024". No real vehicle data from OBD/API.
7 | Home / Map | Fuel % health chip | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Chip exists — hardcoded 65%. Needs real OBD fuel sensor value.
8 | Home / Map | Battery health chip (Good/Bad) | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Chip exists — hardcoded "Good". Needs real voltage read from OBD.
9 | Home / Map | Engine status chip (check engine) | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Chip exists — hardcoded "Good". Needs real MIL/DTC status from OBD.
10 | Home / Map | Device connection chip (OBD online/offline) | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Chip exists — hardcoded "Good". Needs actual device last-seen ping from API.
11 | Home / Map | Vehicle card context menu (Notif / Details / Driving Stats) | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | Bouncie's 3-dot on vehicle card opens: Notification Settings, Vehicle Details, Driving Stats. Tracklynk has no such menu.
12 | Home / Map | Map type toggle (Road / Satellite) | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | Bouncie has Road/Satellite picker in map options panel. Not started in Tracklynk.
13 | Home / Map | Live Traffic overlay | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | Google Maps traffic layer is not enabled. One-line change once data pipeline is live.
14 | Home / Map | Speed Legend overlay | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | Shows colour key for speed bands on map. Not started.
15 | Home / Map | Geo-Zone Areas overlay on map | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Bouncie overlays active geofence circles on map. No geofencing built in Tracklynk.
16 | Home / Map | Vehicle pin tap → action sheet (Apple Maps / Google Maps / Uber / Lyft) | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | Tapping Bouncie's vehicle pin shows action sheet with navigation/ride apps. Nothing in Tracklynk.
17 | Home / Map | Multiple vehicle switcher | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | Dropdown UI exists on header. Only 1 mock vehicle. Needs multi-vehicle data model.
18 | Home / Map | Conversational AI assistant (Tracklynk exclusive) | ✗ No | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | EXCLUSIVE TO TRACKLYNK. Expandable bottom sheet with AI quick-actions. UI built, responses are mocked only.
TRIPS LIST
19 | Trips List | Day View — all trips overlaid on single map for the day | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P2 | V2 | Bouncie's second signature feature (v4.15, Sept 2025). Tracklynk shows individual cards. Day View not started.
20 | Trips List | Daily aggregate stats (X trips · Y miles · VIEW DAY button) | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P2 | V2 | Bouncie groups trips by day and shows aggregate before you drill in. Tracklynk has no daily summary row.
21 | Trips List | Individual trip rows (start time → end time, distance) | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Trips.jsx has 6 mock trip cards. No real trip data. Needs Bouncie /trips API endpoint.
22 | Trips List | Trip list date grouping | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Date grouping structure exists in Trips.jsx with mock dates. Works visually.
23 | Trips List | Trip filter by date range | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | Filter sheet UI built with date radio buttons. No real filtering against API data.
24 | Trips List | Trip overflow menu (share, delete, flag) | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P2 | V2 | Bouncie has '...' on each trip row. Tracklynk has no per-trip actions.
TRIP DETAIL
25 | Trip Detail | Route replay polyline on map | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | TripDetail.jsx renders polyline via Google Maps. Coordinates are mock arrays. Needs real GPS breadcrumb from API.
26 | Trip Detail | Color-coded speed bands (green/yellow/red vs posted limit) | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | CRITICAL GAP. Bouncie's #1 feature. Tracklynk route is single lime color. Need segmented polylines with speed-vs-limit logic.
27 | Trip Detail | Safety / driving score gauge (0–100, A/B/C/D) | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | SVG circular gauge built in TripDetail.jsx with color coding. Value is hardcoded mock. Needs real score calculation.
28 | Trip Detail | Hard braking events with timestamp + count | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Event badge exists with icon and mock count. Needs real OBD event data.
29 | Trip Detail | Rapid acceleration events with timestamp + count | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Event badge exists. Mock data only.
30 | Trip Detail | Speed alert events on route | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Event badge exists. Mock data only.
31 | Trip Detail | Trip stats (distance, duration, idle time) | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Stats shown in trip detail. All hardcoded. Needs real trip data from API.
32 | Trip Detail | MPG / fuel economy per trip | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | MPG displayed as mock value. Needs real OBD fuel consumption data.
33 | Trip Detail | Max speed for the trip | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Bouncie shows max speed on trip. Not displayed in Tracklynk's trip detail screen.
34 | Trip Detail | Start/end address labels on route | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Start (lime) and end (red) markers exist. Labels are hardcoded. Needs real reverse-geocoding.
OBD HEALTH DRILL-DOWN
35 | OBD Health Drill-Down | Fuel detail screen (large dial + notification threshold) | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Bouncie: full screen with fuel % dial, alert threshold config. Tracklynk: chip only, no drill-down at all.
36 | OBD Health Drill-Down | Battery detail screen (voltage value + Normal/Low/Critical thresholds) | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Bouncie explains 12.6V=Normal, 12V=Low. This IS the battery voltage improvement you identified as a competitive win. Not started.
37 | OBD Health Drill-Down | Engine / DTC codes screen (code + plain-English description) | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Bouncie: "All Good! No trouble codes found" + DTC notification toggle. Tracklynk: no drill-down screen.
38 | OBD Health Drill-Down | Device status screen (IMEI, serial number, last comm timestamp + location) | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Bouncie: shows IMEI, serial, last ping time, last known address. Tracklynk: chip only.
NOTIFICATION CENTER
39 | Notification Center | Drive tab (Hard Braking, Rapid Accel, Curfew, Trip Start/End, Speed) | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Bouncie's Drive tab is the core alert feed. Zero notification infrastructure in Tracklynk.
40 | Notification Center | Vehicle tab (Impact, Fuel Low, Battery, Geo-fence, DTC, Tamper, Distance, Idle) | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | 8 distinct vehicle alert types in Bouncie. None built in Tracklynk.
41 | Notification Center | Care tab (Distance, Idle Time, Trip Fuel Economy, Battery, DTC, Tamper) | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P2 | V2 | Care-specific notification history tab. Not started.
42 | Notification Center | Push notification delivery (FCM / APNs) | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Zero push infrastructure. This is the #1 blocker for all alert features. Must be built first.
ALERT CONFIGURATION
43 | Alert Configuration | Hard Braking config (toggle + Excessive / Moderate / Light) | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Bouncie has 3-level segmented control. Tracklynk has placeholder toggle in Settings — no config screen.
44 | Alert Configuration | Rapid Acceleration config (toggle + 3-level sensitivity) | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Same pattern as hard braking. Not started.
45 | Alert Configuration | Speed alert config (Speed Limit + Speed Bands + Excessive MPH threshold) | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Bouncie has 3 separate speed settings. Not started in Tracklynk.
46 | Alert Configuration | Geo-Zone creation screen (circular zone, name, schedule) | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Bouncie: "Create Geo-Zone" with circular zone builder. Zero geofencing logic in Tracklynk.
47 | Alert Configuration | Curfew creation screen (time window) | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P2 | V2 | Bouncie: "Create Curfew" with time range. Non-functional toggle in Tracklynk Settings.
48 | Alert Configuration | Trip Start / Trip End config (separate toggles) | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Bouncie has independent toggles for trip-start and trip-end alerts. Not started.
49 | Alert Configuration | Fuel Level alert slider (threshold %) | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Bouncie: arc slider defaulting to 15%. Not started.
50 | Alert Configuration | Battery alert config (Low & Critical / Critical Only toggle) | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | Bouncie: two-mode battery alert. Not started.
51 | Alert Configuration | Distance Driven alert slider (mile threshold) | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P2 | V2 | Bouncie: arc slider defaulting to 400 miles. Not started.
52 | Alert Configuration | Idle Time alert config (Start/End + Total options) | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P2 | V2 | Bouncie: two idle time options. Not started.
53 | Alert Configuration | NWS Weather alert toggle | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P2 | V2 | Bouncie: simple push toggle for NWS alerts near vehicle. Not started.
54 | Alert Configuration | Impact Detection + emergency SMS contact | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P2 | V2 | Bouncie: toggle + 'Who should receive Accident SMS'. Needs contacts data model + Twilio.
55 | Alert Configuration | DTC / Check Engine push toggle | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Bouncie: simple push toggle for check engine events. Not started.
56 | Alert Configuration | Tamper Detection toggle (OBD unplugged) | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | Bouncie: fires when adapter removed then reconnected. Not started.
SETTINGS / PROFILE
57 | Settings / Profile | My Profile screen (email, phone, password, Face ID) | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | ProfileEditView fully built — first/last name, email, phone, avatar, save with animation. No backend.
58 | Settings / Profile | Delete Account | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | DeleteAccountView fully built — confirmation flow with 2-step verification. No backend wired.
59 | Settings / Profile | Vehicles management (add / edit / remove) | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | VehicleDetailView + AddVehicleView both fully built — edit nickname/plate, OBD device card, remove with confirmation flow.
60 | Settings / Profile | Subscription management | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P2 | V2 | SubscriptionMain + SwitchPlanView + CancelFlowView all fully built. No Stripe integration.
61 | Settings / Profile | Payment details (billing history, payment method) | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P2 | V2 | PaymentMethodView fully built — card fields, billing history. No real payment processor.
62 | Settings / Profile | Units setting (Imperial / Metric, MPG / L/100km / km/L) | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | Not found in Settings.jsx. Bouncie has dedicated Units screen. Not started.
63 | Settings / Profile | App Appearance (Light / Dark / System with visual previews) | ✓ Yes | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | Not found in Settings.jsx. No in-app theme toggle built.
64 | Settings / Profile | Support / live chat | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P2 | V2 | HelpSupportView fully built — FAQ accordion, contact options. No live chat backend.
65 | Settings / Profile | Feedback submission | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P2 | V2 | Feedback option in HelpSupportView. UI only.
66 | Settings / Profile | Privacy Policy / Terms of Service | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | TermsPrivacyView fully built — tabbed Terms + Privacy with full legal text content.
67 | Settings / Profile | App version display | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | Version 1.0.0 shown in WhatsNewView sublabel. Not shown on main settings screen.
—
— | Settings / Profile | Two-Factor Authentication setup flow | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | TwoFactorView fully built — enable/disable 2FA, verification code entry flow. No backend.
— | Settings / Profile | Active Sessions management (view + revoke devices) | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | ActiveSessionsView fully built — lists 3 mock devices with revoke option. No real session data.
— | Settings / Profile | Privacy & Data controls | ✓ Yes | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | PrivacyDataView fully built — data export, analytics toggles. No backend wired.
— | Settings / Profile | What's New / Changelog screen | ✗ No | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | WhatsNewView fully built — versioned changelog. Tracklynk exclusive (Bouncie has no equivalent in-app).
ONBOARDING FLOW |  |  |  |  | — | — | — | —
68 | Onboarding Flow | Welcome carousel (hero / features / pricing) | ✗ No | ✓ Done | ◑ In Progress | ◑ In Progress | ◑ In Progress | Done | Done | FULLY BUILT. 3-slide carousel with auto-advance, manual swipe, dot navigation.
69 | Onboarding Flow | Auth — Apple / Google OAuth buttons | ✗ No | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | OAuth button UI built. No real authentication backend wired.
70 | Onboarding Flow | Auth — Face ID biometric | ✗ No | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Face ID state machine built in Auth.jsx (idle→scanning→verified). Mock only.
71 | Onboarding Flow | Sign Up (email + password with validation) | ✗ No | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Form built with live validation in SignUp.jsx. No backend account creation.
72 | Onboarding Flow | Add Vehicle — VIN barcode scan | ✗ No | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Scan animation UI built. No camera access or real barcode parsing.
73 | Onboarding Flow | Add Vehicle — manual VIN entry fallback | ✗ No | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Manual input field exists. No VIN validation or vehicle lookup API.
74
75 | Onboarding Flow | OBD device scan + Bluetooth pairing | ✗ No | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Animated scan UI built. No real Bluetooth or device communication.
76 | Onboarding Flow | Device setup wizard (step-through with OBD port illustration) | ✗ No | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Multi-step animation built. No actual device connectivity.
77 | Onboarding Flow | Choose Plan (monthly / annual toggle, animated price) | ✗ No | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P0 | V1 Core | Plan selection UI built. No Stripe / RevenueCat integration.
78 | Onboarding Flow | Success screen (checkmark + next-steps checklist) | ✗ No | ✓ Done | ◑ In Progress | ◑ In Progress | ◑ In Progress | Done | Done | FULLY BUILT. Animated checkmark, confetti, next-steps checklist.
TRACKLYNK EXCLUSIVE
79 | Tracklynk Exclusive | Conversational AI assistant with quick-action pills | ✗ No | ◑ Partial | ✗ Not Started | ✗ Not Started | ✗ Not Started | P1 | V1 Polish | Bouncie has NO AI assistant. This is Tracklynk's strongest differentiator. UI built, responses are mocked. Needs real LLM integration.
80 | Tracklynk Exclusive | Dark-first UI theme (premium feel vs Bouncie's flat white) | ✗ No | ✓ Done | ◑ In Progress | ◑ In Progress | ◑ In Progress | Done | Done | Consistent dark glassmorphism aesthetic. Bouncie is plain white/light. Clear visual differentiation.
81 | Tracklynk Exclusive | Framer Motion micro-interactions & spring animations | ✗ No | ✓ Done | ◑ In Progress | ◑ In Progress | ◑ In Progress | Done | Done | All screens use spring-based animations. Bouncie has flat, static transitions. UX quality advantage.
SUMMARY |  |  |  |  | — | — | — | —
| Total Features Mapped | 84 |  |  | — | — | — | —
| ◑ Partial (UI/Mock) | 43 |  |  | — | — | — | —
| ✗ Not Built | 37 |  |  | — | — | — | —
| % Complete (weighted) | 30.4 |  |  | — | — | — | —
PROGRESS BY SCREEN |  |  |  |  | — | — | — | —
Screen | Total | ✓ Done | ◑ Partial | ✗ Not Built | ✗ Not Started | ✗ Not Started | ✗ Not Started | — | % Complete | Priority
Home / Map | 18 | 0 | 10 | 8 | — | — | — | — | 27.8 | P0 — Ship first
Trips List | 6 | 0 | 3 | 3 | — | — | — | — | 25 | P0 — Ship first
Trip Detail | 10 | 0 | 8 | 2 | — | — | — | — | 40 | P0 — Ship first
OBD Health Drill-Down | 4 | 0 | 0 | 4 | — | — | — | — | 0 | P0 — Ship first
Notification Center | 4 | 0 | 0 | 4 | — | — | — | — | 0 | P0 — Blocks all alerts
Alert Configuration | 14 | 0 | 0 | 14 | — | — | — | — | 0 | P1 — After notif infra
Settings / Profile | 15 | 0 | 13 | 2 | — | — | — | — | 43.3 | P1
Onboarding Flow | 10 | 2 | 8 | 0 | — | — | — | — | 60 | P1 — Needs backend
Tracklynk Exclusive | 3 | 2 | 1 | 0 | — | — | — | — | 83.3 | P1 — Differentiator

## _Lists (hidden)
Status | Priority | Phase
✓ Done | P0 | V1 Core
◑ In Progress | P1 | V1 Polish
✗ Not Started | P2 | V2
| Done | Done
TBD