## Slide 1
TRACKLYNK
Implementation Gantt Chart
4
Phases
~11w
AI-Assisted
~26w
Standard
Frontend and backend delivered in parallel within each phase
Phase 1: Base App + Tracking
Auth (OAuth, email, Face ID)
Vehicle + OBD device pairing
Live GPS map (15s polling)
Trip recording & history
Phase 2: Bouncie Feature Parity
Color-coded speed bands on routes
OBD health drill-down screens
Push notifications (FCM + APNs)
Alert rules engine (14 alert types)
Phase 3: Differentiators
AI assistant with real LLM backend
Maintenance care plan + reminders
Impact detection + auto-SMS
Polygon geofencing + dark mode
Phase 4: Optimization & Rollout
iOS + Android app store launch
Public REST API + OAuth 2.0
Developer portal + webhooks
Performance, CI/CD + monitoring

## Slide 2
AI-Assisted Timeline
~11 weeks total · 1 frontend + 1 backend developer · FE and BE run in parallel within each phase
W0
W1
W2
W3
W4
W5
W6
W7
W8
W9
W10
W11
Phase 1
Base App + Tracking
Auth (OAuth, email, Face ID)
Vehicle + OBD device pairing
Live GPS map (15s polling)
Trip recording & history
Stripe / RevenueCat payments
FE
BE
Phase 2
Bouncie Feature Parity
Color-coded speed bands on routes
OBD health drill-down screens
Push notifications (FCM + APNs)
Alert rules engine (14 alert types)
Geofencing + notification center
FE
BE
Phase 3
Differentiators
AI assistant with real LLM backend
Maintenance care plan + reminders
Impact detection + auto-SMS
Polygon geofencing + dark mode
Battery voltage trend graphs
FE
BE
Phase 4
Optimization & Rollout
iOS + Android app store launch
Public REST API + OAuth 2.0
Developer portal + webhooks
Performance, CI/CD + monitoring
Crash tracking + analytics pipeline
FE
BE
2w
2.5w
2.5w
3.5w
2w
2.5w
1.5w
2w
LEGEND
FE — lighter shade
BE — deeper shade
Phase Transition

## Slide 3
Standard Timeline
~26 weeks (~6.5 months) total · 1 frontend + 1 backend developer · FE and BE run in parallel within each phase
W0
W2
W4
W6
W8
W10
W12
W14
W16
W18
W20
W22
W24
W26
Phase 1
Base App + Tracking
Auth (OAuth, email, Face ID)
Vehicle + OBD device pairing
Live GPS map (15s polling)
Trip recording & history
Stripe / RevenueCat payments
FE
BE
Phase 2
Bouncie Feature Parity
Color-coded speed bands on routes
OBD health drill-down screens
Push notifications (FCM + APNs)
Alert rules engine (14 alert types)
Geofencing + notification center
FE
BE
Phase 3
Differentiators
AI assistant with real LLM backend
Maintenance care plan + reminders
Impact detection + auto-SMS
Polygon geofencing + dark mode
Battery voltage trend graphs
FE
BE
Phase 4
Optimization & Rollout
iOS + Android app store launch
Public REST API + OAuth 2.0
Developer portal + webhooks
Performance, CI/CD + monitoring
Crash tracking + analytics pipeline
FE
BE
5w
6w
7w
9w
5w
6w
4w
5w
LEGEND
FE — lighter shade
BE — deeper shade
Phase Transition