TRACKLYNK

Multi-Phase Implementation Plan

This document outlines the four-phase implementation roadmap for Tracklynk, a smart vehicle tracking platform. Each phase pairs frontend and backend work to ship complete, usable functionality — not half-built screens.

| Phase | Name | Goal |
| --- | --- | --- |
| 1 | Base App + Tracking | A real working app — auth, vehicle registration, GPS on map, trip history |
| 2 | Bouncie Feature Parity | Match every Bouncie feature — alerts, OBD health, geofencing, notifications |
| 3 | Differentiators | AI assistant, maintenance plan, impact detection, exclusive UX advantages |
| 4 | Optimization & Rollout | Performance, public API, app store, monitoring, scale |

PHASE 1 Base App + Nominal Vehicle Tracking Get a real, shippable app into users' hands

## Overview

Everything in the current prototype is fake — hardcoded coordinates, mock trips, no login persistence. Phase 1 makes the foundation real. A user can sign up, add their vehicle, pair their OBD device, pay for a plan, and see their car on a live map. Sessions persist on relaunch. This is the version you test with early users.

## Frontend Work

### Auth & Session Management

- Wire Apple/Google OAuth buttons to real OAuth SDK calls

- Connect Sign Up form to /auth/register API endpoint

- Implement JWT token storage — secure, not localStorage

- Session check on app boot — route to Welcome or Home based on token state

- Token expiry handling and silent refresh flow

- Face ID biometric wiring (UI already built, needs native API connection)

### Protected Routing

- Replace flat state machine in App.tsx with a proper auth gate

- Unauthenticated users → Onboarding flow

- Authenticated users → Main app (Home / Trips / Settings)

### Onboarding Flow Wiring

- AddVehicle: VIN input → POST to backend → receive vehicle record

- ScanDevice + DeviceSetupWizard: OBD pairing connected to device registration API

- ChoosePlan: Payment intent creation via Stripe / RevenueCat

- Success screen only renders after backend confirms vehicle + device linked

### Live Map (Home Screen)

- Replace hardcoded coordinates with real vehicle location from API

- 15-second polling mechanism to refresh vehicle pin position

- Recenter button pans to actual vehicle location

- Live Trip badge shown only when a trip is actively in progress

### Trips List

- Replace mock trips with real trip history from backend

- Real distance, duration, start/end address per trip card

- Empty state shown when no trips recorded yet

### Settings

- Profile edit (name, email, avatar) wired to PATCH /user/me

- Avatar upload to cloud storage

- Units toggle (Imperial/Metric) persisted to user preferences

- Delete account 2-step confirmation wired to backend

## Backend Work

| Auth & User APIs | Vehicle, Tracking & Payment |
| --- | --- |
| POST /auth/register — email + password | GET /vehicles — list user vehicles |
| POST /auth/login — return JWT pair | POST /vehicles — create vehicle (VIN decode) |
| POST /auth/oauth/apple — Apple token verify | PATCH /vehicles/:id — edit vehicle |
| POST /auth/oauth/google — Google token exchange | DELETE /vehicles/:id — remove vehicle |
| POST /auth/refresh — silent token refresh | POST /vehicles/:id/device — pair OBD device |
| POST /auth/logout — invalidate refresh token | GET /vehicles/:id/location — latest GPS position |
| GET/PATCH /user/me — profile | GPS polling worker — 15-second interval, upsert position |
| PUT /user/me/avatar — cloud upload | Trip recording — detect start/end, store route |
| PATCH /user/me/preferences — units, settings | GET /trips — paginated trip history |
| DELETE /user/me — account deletion | Stripe/RevenueCat — subscription creation + webhooks |

EXIT CRITERIA - User can sign up with email or OAuth (Apple/Google) and stay logged in across app relaunches - Vehicle is added via VIN, OBD device is paired, plan is selected and paid - Home screen shows real vehicle pin at actual GPS location, updating every 15 seconds - Trips list shows real completed trips with accurate distance and duration - Settings profile save persists across sessions

PHASE 2 Feature Parity with Bouncie Close every gap — no reason to pick them over Tracklynk

## Overview

Phase 1 gives you a working tracker. Phase 2 gives you a competitive product. Every major Bouncie feature gets built here — speed bands on route replay, all alert types, geofencing, OBD health drill-down, push notifications, and a full notification center. By the end of Phase 2, Tracklynk matches Bouncie feature-for-feature.

## Frontend Work

### Trip Route Replay with Speed Bands

- Color-coded polyline on route replay: green (0–35 mph), yellow (35–65 mph), red (65+ mph)

- This is Bouncie's #1 signature feature — the single most visible gap right now

- Trip detail screen (new): full-screen map, stats row, start/end addresses

- Route scrubber: tap any point → see speed and timestamp at that moment

### OBD Health Screens (all new — currently 0% built)

- Health summary card on Home screen, tappable to drill down

- Fuel level screen with current percentage and trend

- Battery voltage screen with current reading and 7/30-day trend graph

- DTC fault codes screen — code + plain-English description per code

- Check engine light indicator — prominent, tappable, links to DTC screen

- Device status screen — signal strength, last ping time, firmware version

### Notification Center (new — currently 0% built)

- Three tabs: Drive / Vehicle / Care

- Drive tab: speeding, hard braking, rapid acceleration, idle events

- Vehicle tab: geofence entry/exit, check engine, low battery

- Care tab: maintenance due, oil change, scheduled service

- Mark as read, clear all, tap to deep-link to relevant screen

### Alert Configuration (14 features — all currently 0% built)

- Speed threshold alert — set mph limit

- Hard braking and rapid acceleration sensitivity toggles

- Idle alert — set duration threshold

- Geofence setup — draw circle zone on map

- Geofence rules — trigger on entry / exit / both

- Curfew alert — set allowed time window

- Low battery threshold setting

- Per-alert: push notification on/off, SMS on/off

### Push Notifications

- FCM (Android) + APNs (iOS) handler inside the app

- Foreground: in-app toast/banner for live alerts

- Background: native system notification, tapping deep-links into app

## Backend Work

| Tracking & OBD | Notifications & Alerts |
| --- | --- |
| GPS stream processing — speed classification per point | FCM + APNs integration (Firebase recommended) |
| Speed band tagging stored with route (slow/moderate/fast) | POST /user/devices/push-token — register device token |
| OBD telemetry ingestion — fuel, battery, DTC, RPM, coolant temp | Notification dispatch queue (async, not synchronous) |
| DTC decoder — raw codes to plain-English descriptions | Notification history storage (sent/read state) |
| GET /vehicles/:id/obd — current health snapshot | Alert rules engine — evaluate telemetry against user rules |
| GET /vehicles/:id/obd/history — trend data for graphing | Deduplication — prevent repeated alerts for same condition |
| Time-series storage for battery voltage history | GET/POST/PATCH /alerts/config — alert rule CRUD |
|  | Geofencing service — store zones, evaluate on each location update |
|  | GET /notifications — paginated, filterable by tab |
|  | PATCH /notifications/:id/read, /notifications/read-all |

EXIT CRITERIA - Tapping a completed trip shows the route with green/yellow/red speed bands - OBD health screen shows real fuel level, battery voltage, and DTC codes - User receives a push notification when vehicle exceeds configured speed threshold - Geofence entry/exit triggers a notification and appears in Notification Center - Alert configuration screen saves rules that actually fire

PHASE 3 Differentiators The reasons someone picks Tracklynk over every competitor

## Overview

Phase 2 gets you to parity. Phase 3 builds the moat. These are the features Bouncie either doesn't have or executes poorly — an AI assistant that understands your vehicle, maintenance intelligence, accident detection, and the premium UX that makes Tracklynk feel like a different category of product.

## Frontend Work

### Conversational AI Assistant (UI built — currently fully mocked)

- Wire chat input to real LLM backend with vehicle context

- AI can answer: 'Why did I get a check engine light?' → pulls DTC, explains plainly

- AI knows: recent trips, current OBD data, active alerts, vehicle history

- Streaming response for instant chat feel

- KPI strip on the panel shows real live data — speed, battery, trip status

### Maintenance Care Plan (all new — currently 0% built)

- Maintenance schedule screen — oil change, tire rotation, brake check, air filter

- Mileage-based and time-based reminder intervals

- Mark service as done → resets interval counter

- Service history log

- Overdue alerts appear in Notification Center (Care tab)

### Accident / Impact Detection

- Impact event card in Notification Center

- Auto-SMS preview — shows message and recipient (emergency contact)

- Emergency contact setup in Settings

### Battery Voltage Trend Graph

- Recharts line chart (already in the dependency tree)

- 7-day / 30-day toggle

- Warning threshold line at 12.4V

### Additional Differentiator Features

- Dark / Light / System mode toggle — wired to MUI theme switching, persisted

- Engine-off hourly GPS pings — 'Vehicle last seen X hours ago at [address]'

- Polygon geofencing — draw custom shapes, not just circles

- What's New changelog screen — needs real content pipeline

## Backend Work

| AI & Maintenance | Safety & Advanced Tracking |
| --- | --- |
| LLM API integration (GPT-4o or Claude API) | Accelerometer / g-force spike analysis on telemetry |
| System prompt primed with vehicle context per user | Impact event classification and storage |
| POST /ai/chat — stateless or stateful conversation endpoint | Auto-SMS dispatch via Twilio or equivalent |
| Rate limiting per user on AI endpoint | Emergency contact management endpoint |
| Streaming response support (SSE or WebSocket) | GET /vehicles/:id/impact-events — impact history |
| Maintenance schedule CRUD per vehicle | Battery voltage time-series — extended history for trend graphs |
| Mileage delta tracking from trip data | Engine-off ping scheduling — hourly location capture when ignition off |
| Due-soon detection → triggers notification pipeline | Polygon geofencing — store/evaluate arbitrary shapes |
| Service log storage and history endpoint | Changelog CMS or static content endpoint |

EXIT CRITERIA - Conversational AI answers real questions about the user's vehicle using live data - Maintenance reminders fire correctly based on mileage and time intervals - Impact detection logs an event and auto-SMS fires to the emergency contact - Battery voltage trend graph renders real historical data - Dark/light mode toggle works and persists across sessions

PHASE 4 Optimization & Rollout Make it bulletproof. Open it up. Ship it.

## Overview

Phase 4 is not about new features — it's about making everything that exists fast, reliable, and ready for public scale. This includes the public REST API that lets third-party developers build on Tracklynk, app store submission, and the monitoring infrastructure needed to operate confidently at scale.

## Frontend Work

### Performance

- Map rendering optimization — reduce re-renders on location updates

- Cold start time reduction — lazy loading, code splitting

- List virtualization on Trips screen for large trip histories

- Animation performance audit — ensure 60fps on mid-range devices

### App Store Preparation

- iOS and Android build configuration

- App store screenshots, metadata, and preview video

- Push notification permission flow — correct native prompting

- Deep link handling for all notification tap destinations

### Polish & Edge Cases

- Offline state handling — graceful degradation when no connectivity

- Empty states for all screens (trips, notifications, health data)

- Error boundaries — app should never show a white screen

- Loading skeletons on all data-fetching screens

## Backend Work

### Public REST API with OAuth 2.0

- OAuth 2.0 authorization server (authorization code flow)

- Scoped API tokens — read:location, read:trips, write:alerts, etc.

- Public endpoints: GET /v1/vehicles, /v1/trips, /v1/location

- Rate limiting and API key management

- Webhook support — push events to developer endpoints instead of polling

- Developer portal with API documentation

### Infrastructure & Reliability

- Crash monitoring — Sentry or equivalent on client and server

- Analytics pipeline — DAU, trip frequency, alert fire rate, feature usage

- Load testing — GPS polling service and alert rules engine under concurrent users

- Database indexing audit — trips and location history queries at scale

- CI/CD pipeline — automated tests on PR, deploy on merge to main

EXIT CRITERIA - App cold start time is under 2 seconds on a mid-range device - iOS and Android builds pass app store review and are live in both stores - A third-party developer can authenticate via OAuth 2.0 and pull trip data from the public API - Crash rate is below 0.1% on 7-day rolling average - All screens handle empty, loading, error, and offline states without crashing

# Dependency Chain

Phases are strictly ordered. Each one unlocks the next.

| Phase | Unlocks | Hard Dependency |
| --- | --- | --- |
| Phase 1 | Real users, real vehicles, live map | Everything. Nothing else works without auth and a real data pipeline. |
| Phase 2 | Alerts, OBD health, notifications | Requires real GPS stream (Phase 1). Push infra needs device tokens from auth. |
| Phase 3 | AI, maintenance, impact detection | AI needs real OBD + trip data (Phase 2). Maintenance needs trip mileage tracking. |
| Phase 4 | Public API, app store, scale | Requires all features stable. Public API exposes Phase 1–3 data. |

# Effort Estimation

Two scenarios are provided: a standard development timeline with a dedicated 2-person team (1 frontend + 1 backend), and an AI-assisted timeline leveraging code generation tooling throughout. Duration reflects wall-clock weeks with both roles working in parallel. A 20–25% buffer should be added for unknowns in each phase.

## Standard Timeline

Assumes 1 frontend developer + 1 backend developer working full-time in parallel. Does not include design, QA buffer, or DevOps setup time.

| Phase | Frontend Effort | Backend Effort | Duration (parallel) |
| --- | --- | --- | --- |
| Phase 1 — Base App + Tracking | 5 weeks | 6 weeks | 6 weeks |
| Phase 2 — Bouncie Feature Parity | 7 weeks | 9 weeks | 9 weeks |
| Phase 3 — Differentiators | 5 weeks | 6 weeks | 6 weeks |
| Phase 4 — Optimization & Rollout | 4 weeks | 5 weeks | 5 weeks |
| TOTAL | 21 person-weeks | 26 person-weeks | ~26 weeks (~6.5 months) |

## AI-Assisted Timeline

Leverages AI code generation tooling throughout — for boilerplate, API wiring, CRUD services, screen generation, and test scaffolding. The human developer directs, reviews, and makes architecture calls. Complex logic and external service setup are only partially accelerated.

| Phase | Frontend Effort | Backend Effort | Duration (parallel) |
| --- | --- | --- | --- |
| Phase 1 — Base App + Tracking | 2 weeks | 2.5 weeks | 2.5 weeks |
| Phase 2 — Bouncie Feature Parity | 2.5 weeks | 3.5 weeks | 3.5 weeks |
| Phase 3 — Differentiators | 2 weeks | 2.5 weeks | 2.5 weeks |
| Phase 4 — Optimization & Rollout | 1.5 weeks | 2 weeks | 2 weeks |
| TOTAL | 8 person-weeks | 10.5 person-weeks | ~11 weeks (~3 months) |

## What Accelerates vs What Doesn't

| Speeds up 3–4x | Speeds up 1.5–2x |
| --- | --- |
| REST endpoint generation + data models | Alert deduplication + geofence polygon math |
| Auth service boilerplate (JWT, OAuth flows) | LLM context management + prompt engineering |
| CRUD operations across all services | OAuth 2.0 authorization server implementation |
| Form wiring + API connection in frontend | Integration bugs between services |
| Test scaffolding + type definitions | Impact detection algorithm edge cases |
| Component-to-API data binding | Performance optimization (profiling-dependent) |

NOT ACCELERATED — Real-world friction that no tooling removes Stripe / FCM / APNs / Apple developer account setup and approval. App store review (Apple: 1–3 days minimum). Architecture and product decisions — a human still makes those calls. QA and user testing — automated tests help, but real user feedback takes real time. The developer's bandwidth to review, direct, and course-correct is always the actual bottleneck.